## BILL OF QUANTITY
RFQ FOR CIVIL WORKS FOR TELECOMMUNICATION CABIN WORKS FOR ALLO TECHNOLOGY SDN. BHD. IN PMU BUKIT BATU
Purpose: Construction of concrete slab for Cabin, concrete footing for Anti-Climb Fencing and any other related civil works to complete the installation according to ALLO specifications at PMU Bukit Batu ( BBTU )
Location: Pencawang Masuk Utama ( PMU ) 500/275/132kV Bukit Batu ( BBTU )
Project Duration : 4 Days ( 13 January 2025 - 16 January 2025 )
No | Description | U.O.M | Quantity | Unit Price (RM) | Total Price (RM)
A | Mobilization, preliminaries, site clearing, demolish of existing cabin structure, relocation of mainhole ( JRC7 ) and make good of impacted area inclusive of
1 | Mobilization Cost - South Includes mobilization of manpower with valid NTSP and CIDB, equipment and tools, administrative charges and all other overheads for a site in Johor | EA | 1 |  | 0
2 | Utility Mapping Johor The rate is inclusive of site preparation, safety consideration, cost of usage of equipment, submission of drawings for endorsement from license surveyor or competent person and other items to complete the job according to TNB and/or local authority's requirement. ( 9m x 7m = 63m2) | m2 | 63 |  | 0
3 | Clearing of site all vegetation, trees, shrubs, under growth, hacking and dispose existing reinforced concrete slab of structure foundation including complete grubbing and cart away to contractor's own dumpsite | Lot | 1 |  | 0
4 | Backhoe excavator / loader for site work activity ( Demolish existing concrete slab, Site Clearing, Excavation, Levelling, Relocation of Mainhole JRC7 & Making good of site ) | Days | 2 |  | 0
B | Foundation for cabin structure and Anti-Climb Fencing Pole. Rate include excavation, levelling with crusher run, sawn formwork to slab size, high yield reinforcing Fabric of Steel ( BRC ), Installation of PVC pipe for service pit (PVC pipe taken from existing cabin concrete slab), lean readymix concrete for cabin slab and fencing pole
1 | Backfilling and levelling with crusher run and sand for Cabin compound ( 8.4m x 6.6m x 0.1m ) | Ton | 10 |  | 0
2 | BRC A7 (BS SIRIM JKR FULL SPEC) - 6meter X 2.2meter Reinforcing Fabric of Steel | Nos | 2 |  | 0
3 | Standard Grade Ready Mixed Concrete Grade 25 for Cabin Concrete Slab and Anti-Climb Pole Fencing | m3 | 7 |  | 0
4 | Formwork according to concrete slab dimension ( 4.3m x 6.1m x 0.2m) | Set | 1 |  | 0
5 | Soil digging ( 0.45m x 0.45m ), erection of Anti-Climb Fencing Pole ( Fencing Pole to be supply by ALLO Cabin Contractor ) and pouring of ready mixed concrete grade 25 | Nos | 12 |  | 0
C | Supply & installation of Grounding system inclusive of Threaded Copper Rod c/w Rod Couplings, Exothemic Welding, Annealed Copper Tape - 25mm x 3mm to grounding point laid underground. ( Heavy Duty Concrete Earth Chamber to be supply by ALLO Cabin Contractor ). Scope inclusive of ground resistance testing (Minimum requirement 5 Ohm or less)
1 | 5/8" x 1800mm Threaded Copper Rod ( 3 Copper Rod per Earth Point ) | Nos | 15 |  | 0
2 | 5/8" Rod Coupling ( 2 Rod Coupling per Earth Point ) | Nos | 10 |  | 0
3 | 25mm x 3mm Annealed Copper Tape / Copper Strip | Meter | 30 |  | 0
4 | Thermo-cadwelding | EA | 5 |  | 0
Grand Total Price Inclusive of All Applicable Taxes and Duties, Including Sales & Services Tax (RM) |  |  |  |  | 0
Compliance Term |  |  |  | (Yes/No)
Qualification: 1. Registered as a vendor with Tenaga Nasional Berhad (TNB) *Please submit Sijil TNB Kontraktor Kerja 2. Contractor must possessed NIOSH TNB Safety Passport (NTSP) and CIDB Green Card *Please submit relevant supporting document
Project Duration : 4 Days (13 January 2025 - 16 January 2025 )
Invoicing Terms : 100% Payment upon work completion and acceptance by Allo Technology.
Payment Term : Within fourty five (45) days upon invoice submission, upon delivery, job completion and acceptance by Allo Technology.
Sign Off by Contractor
I acknowledge that I have read, understand and comply to the above job description in its entirety and capable of performing all of the stated requirements:
Signature:
Name :
Phone Number :
Company Name :
Company's Stamp :
Date :